## Product Summary
Product Name | Tuffybay
Press Release / Pitch | College students go through a lot of materials, and sometimes they only need that specific book for one semester. You have something to sell? A fellow Titan might want to buy it off you! But how would you find them? Tuffybay is the place to meet supply and demand! Sell your equipment in an auction style bid! Want to buy something? Toss in your bid! Or do you need it asap? Buy it now! It is FUN! All buyers and sellers are part of the Titan community, so relax, make friends, and get the product you need from Tuffybay!
(Major) Features | Feature phrase/definition
1 | Buy or sell items in a safe way! All customers are from CSUF!
2 | Vast collection and user friendly catalog! Find the exact item youre looking for with easy filter and search.
3 | Auction based purchaces! Get what you want for the lowest price! Or buy it now with the original price
4 | Post something you want into the wish list! Maybe someone will start selling it when they know you want it!
5 | Customize your preference! Notify when a product is available. Or when its under a certain price. Or even bid automatically to your set price!
Roles
1 | Browser | Anonymous visitors - Take a look on what the community has to offer without registering.
2 | registered user | Users - Can list products for bid and make bids, post and sell items, possible to post comments, evaluate other products and sellers
3 | Community manager | Moderator - Delete inappropiate items, comments and bans users that do not abide by the rules
4 | Customer support | intermediate products if it is out of spec
5 | intermediator | someone realible to pick up the goods and deliver to you.
6 | Website Security | Date protection, authentication, authorization, ect..

## Product Backlog
Type | ID | Rank | Description | Part of | Notes
20 features until 9/17!!! |  |  | Features -> User stories -> Tasks
Feature | F01 | 1 | privacy concern |  | all information is processed on the same server
User story | U01 |  | user can create a profile and the information will be stored safely
Task | T01a | 1 | create login page |  | registered users can post products, not registered can only view
Task | T01b | 1 | send encrypted information send to the server? |  | which information is going to be encrypted?
Task | T01c | 1 | input user data information for login (name, address, ID, credit card... |  | name, nickname, address
User story | U02 |  | User can save profiles (Favories, watchlist, current active bids)
Hash user password
Different authorizations (unlogged, buyer, seller)
Feature | F02 | 1 | Product List is customized
User Story | U02a |  | User can see all products and can filter/search for specific items
User Story | U02b |  | User can see the current bid and cost
User Story | U02c |  | User can click the product to see detailed view of product
User Story | U02d |  | User can save their search customizations
User Story | U02e |  | User can customize the quantity of products listed
Task | T02e |  | limit the quantity of products that can be seen in a page
task | T02e |  | detects the OS and display according to it |  | android? IOS? They have different screen size
Task | T02a |  | create a page to display a product
Task | T02a |  | sort by year
Task | T02a |  | sort by name
Task | T02a |  | sort by color
Task | T02a |  | sort by category
create a product list webpage
Feature | F03 | 2 | User can manage their own profile
User Story | U03a |  | user can change their nickname
User Story | U03b |  | user can change their profile picture
| U03c |  | User can retrieve a password if forgotten
Feature | F04 | 1 | Sell a product
User Story | U04a |  | User can set up product detail, pricing, to sell
User Story | U04b |  | seller input product data |  | seller name, product, photo, address, min/max price,
Task |  | 1 | create a database to host the user profile
Task |  | 1 | create a database to host products profile and associate it with user database |  | must have miniminum and maximum price
See featured / sponsored items
Feature | F05 | 1 | See detailed product page
User Story |  |  | Item name, image, description, rating?, comment?, amount?
User Story |  |  | Authorized users can edit/delete
User Story |  |  | Can bid or purchase
User Story |  |  | Related Products
feature | F06 | 2 | Search engine | F01 | This is part of F02?
User Story |  |  | autocomplete function | F01
User Story |  |  | search with partial words? | F01
User Story |  |  | search by date
feature | F07 | 1 | make a bid (tradtional)
User Story |  |  | See seller name
User Story |  |  | See current bid price
User Story |  |  | display the current user with highest bid
User Story |  |  | Display time until end of bid
User Story |  |  | product description
feature | F08 | 2 | "Buy it now!!!" button | F03 | give the max price and avoid waiting
User Story |  |  | check if user have enough money to buy the product? credit card? app-credits?
feature | F09 | 2 | ask the seller a question
|  | 1 | report a seller / buyer
|  | 4 | check the size of the DB to host all pictures
|  | 5 | resize the photos |  | avoid huge files - how to do it???
|  | 5 | website fee - transactions descriptions |  | 5% fee?
User Story | U01 |  | As a end user, I should be able to use my google cred to login to app | I01 | validate throught csuf email?
User Story | U02 |  | As a end user, I should be able to use my facebook cred to login to app | I01 | validate throught csuf email?
User Story | U03 |  | As a end user, I should be able to create an account based on CSUF email | I01 | i think we should restrict to this one, since it is only for Titans students.
Feature | F10 | 3 | sponsored product/user |  | pay money to have your bid on top (sponsored)
Feature | F11 | 5 | streamer video |  | last in the priority list
Feature | F12 | 4 | Credits can be earned via events? ongoing on campus |  | SURE!
Feature | F13 | 3 | paying with the TITAN card
Feature | F14 | 3 | Countdown timer for a bid
Feature | F15 | 2 | Display products for bid with different kind of filters |  | filters: date, price, type of product, with photo, etc
Feature | F16 | 3 | Seller product modification settings |  | New feature by Kaung
Feature | F17 | 2 | View reviews for each product |  | New feature by Kaung
Feature | F18 | 3 | Shipping option |  | New feature by Kaung
Feature | F19 | 4 | Returns |  | New feature by Kaung
Feature | F20 | 3 | Displaying nested-subcategories for clearer reference |  | New feature by Kaung
|  | 4 | Contact, connect with others
|  | 2 | User can add money to account | Julio Villegas
|  | 2 | User can search for items by type (Buy Now, Auction) | Julio Villegas
|  | 3 | User can select an amount for automatic biding | Julio Villegas
|  | 2 | User can create an alert for new items based on interest | Julio Villegas
|  | 1 | User can ask a seller a question | Julio Villegas
|  | 3 | User can see a list of items by seller | Julio Villegas
|  | 2 | User can rate sellers or buyers | Julio Villegas
|  | 2 | User has a watchlist on the items he is bidding or buying | Julio Villegas
|  | 4 | User can report inadequate items or content | Julio Villegas
|  | 5 | User can split the payment by using two different method of funds | Jose Diaz
|  | 5 | User can pick-up/ship items | Jose Diaz
|  | 4 | Browser can show safe places were user and buyer can meet to make a safe transaction | Jose Diaz
|  | 2 | Verified user can only access the website | Jose Diaz | to avoid scams
|  | 4 | User can use a payment plan to make purchase | Jose Diaz | perfect for students

## Sprint Backlog
|  |  | NOT STARTED | IN PROGRESS | DONE
FEA | USR | TSK | RANK | COMPLEXITY | IN CHARGE | DESCRIPTION | DEPENDENCY | NOTES
F01 |  |  |  |  | Daniel | User registeration and login |  | username, password, email, profile settings
| U01 |  |  |  |  | user can choose between login and sign-up
|  | T01 |  |  |  | create initial webpage that will let the user choose between login and sign-up
|  | T02 |  |  |  | this page will also let the user insert the username/password
|  | T03 |  |  |  | if click login, validate the credentials.
|  | T04 |  |  |  | if click at signup page, redirect to a sign-up page
|  | T05 |  |  |  | to validade credentials, connect to database and check if username/password is a valid combination
|  | T06 |  |  |  | if it is valid, save the username as a global variable (other pages can view and retrieve the username's real name
|  | T07 |  |  |  | if it is not valid, redirect to login page and display a message to try again.
| U02 |  |  |  |  | user can insert their credentials to log in
|  | T01 |  |  |  | create 2 textbox to input username and password.
|  | T02 |  |  |  | Password field must be hidden
|  | T03 |  |  |  | create a button to validade credentials
T04
T05
| U03 |  |  |  |  | user can input their information to sign-up
|  | T01 |  |  |  | create a page to input user information to sign up. Name, Address, phone #, nickname/username, password (hidden). Must check if username is taken and password follow minimal security requirements.
|  | T02 |  |  |  | password must be hidden and must be 2 textbox (1st and 2nd textbox)
|  | T03 |  |  |  | Must check if username is taken. If it is, ask user to choose another username
|  | T04 |  |  |  | Must check if password follow minimal security requirements.
|  | T05 |  |  |  | must check if password is the same (1st and 2nd textbox)
| U04 |  |  |  |  | user will be asked to check their credentials again if username/password did not match
|  | T01 |  |  |  | redirect to login page and display a message that username/password was incorrect
T02
T03
T04
T05
| U05 |  |  |  |  | if user mistake their credentials 3 times, their account will be locked
|  | T01 |  |  |  | set a variable at database to identify if the user is locked or not
|  | T02 |  |  |  | set a global variable to save the number of tries
|  | T03 |  |  |  | if tries > 2, set flag on database as locked. if logged successful, set tries to 0.
T04
T05
| U06 |  |  |  |  | user will have an option to reset password if it is forgotten
T01
T02
T03
T04
T05
| U07 |  |  |  |  | user will have an option to ask for support
T01
T02
T03
T04
T05
| U08 |  |  |  |  | User can register if they have a valid CSUF email |  | website will check CSUF email to confirm that user is a student
|  | T01 |  |  |  | Create database for user data
|  | T02 |  |  |  | Create register page
|  | T03 |  |  |  | Connect database to webpage
|  | T04 |  |  |  | Encrypt connection? hash data?
T05
U09
T01
T02
T03
T04
T05
F02 |  |  |  |  | Euri | Product Listing
| U01 |  |  |  |  | User can see list of products
|  | T01 |  |  |  | Create database for product data? |  | Should this be part of F04? since that contains detailed info
|  | T02 |  |  |  | Make function to fetch product list and return to site
|  | T03 |  |  |  | Create listing page, Display default listing for products | F02-U01-T03 | default = newest products?
|  | T04 |  |  |  | Format: Page > Gallery > Card > Details
T05
| U02 |  |  |  |  | User can search for products by name | F02-U01
|  | T01 |  |  |  | Text input to send to search query
|  | T02 |  |  |  | Make function to send search query to database and fetch return
|  | T03 |  |  |  | Make function to display updated product page
T04
T05
| U03 |  |  |  |  | User can search product list by category |  | Books, equipment
T01
T02
T03
T04
T05
| U04 |  |  |  |  | User can filter product list
T01
T02
T03
T04
T05
| U05 |  |  |  |  | User can click on items to go to details page
T01
T02
T03
T04
T05
| U06 |  |  |  |  | User can sort product list by category |  | Price, sell date, name
T01
T02
T03
T04
T05
U07
T01
T02
T03
T04
T05
U08
T01
T02
T03
T04
T05
U09
T01
T02
T03
T04
T05
F03 | [5 empty] | User profile management | F01
U01
T01
T02
T03
T04
T05
U02
T01
T02
T03
T04
T05
U03
T01
T02
T03
T04
T05
U04
T01
T02
T03
T04
T05
U05
T01
T02
T03
T04
T05
U06
T01
T02
T03
T04
T05
U07
T01
T02
T03
T04
T05
U08
T01
T02
T03
T04
T05
U09
T01
T02
T03
T04
T05
F04 |  |  |  |  | Julio | Product Details
U01
T01
T02
T03
T04
T05
U02
T01
T02
T03
T04
T05
U03
T01
T02
T03
T04
T05
U04
T01
T02
T03
T04
T05
U05
T01
T02
T03
T04
T05
U06
T01
T02
T03
T04
T05
U07
T01
T02
T03
T04
T05
U08
T01
T02
T03
T04
T05
U09
T01
T02
T03
T04
T05
F05 | [5 empty] | Add a product to sell | F01
U01
T01
T02
T03
T04
T05
U02
T01
T02
T03
T04
T05
U03
T01
T02
T03
T04
T05
U04
T01
T02
T03
T04
T05
U05
T01
T02
T03
T04
T05
U06
T01
T02
T03
T04
T05
U07
T01
T02
T03
T04
T05
U08
T01
T02
T03
T04
T05
U09
T01
T02
T03
T04
T05
F06 | [5 empty] | Search product catalog | F02
U01
T01
T02
T03
T04
T05
U02
T01
T02
T03
T04
T05
U03
T01
T02
T03
T04
T05
U04
T01
T02
T03
T04
T05
U05
T01
T02
T03
T04
T05
U06
T01
T02
T03
T04
T05
U07
T01
T02
T03
T04
T05
U08
T01
T02
T03
T04
T05
U09
T01
T02
T03
T04
T05
F07 | [5 empty] | Purchace a product (bid) | F01, F04
U01
T01
T02
T03
T04
T05
U02
T01
T02
T03
T04
T05
U03
T01
T02
T03
T04
T05
U04
T01
T02
T03
T04
T05
U05
T01
T02
T03
T04
T05
U06
T01
T02
T03
T04
T05
U07
T01
T02
T03
T04
T05
U08
T01
T02
T03
T04
T05
U09
T01
T02
T03
T04
T05
F08 | [5 empty] | Add funds to account | F01
U01
T01
T02
T03
T04
T05
U02
T01
T02
T03
T04
T05
U03
T01
T02
T03
T04
T05
U04
T01
T02
T03
T04
T05
U05
T01
T02
T03
T04
T05
U06
T01
T02
T03
T04
T05
U07
T01
T02
T03
T04
T05
U08
T01
T02
T03
T04
T05
U09
T01
T02
T03
T04
T05
F09 | [5 empty] | Have product delivered or meetup | F07
U01
T01
T02
T03
T04
T05
U02
T01
T02
T03
T04
T05
U03
T01
T02
T03
T04
T05
U04
T01
T02
T03
T04
T05
U05
T01
T02
T03
T04
T05
U06
T01
T02
T03
T04
T05
U07
T01
T02
T03
T04
T05
U08
T01
T02
T03
T04
T05
U09
T01
T02
T03
T04
T05
F10 | [5 empty] | Contact seller, message | F01, F04
U01
T01
T02
T03
T04
T05
U02
T01
T02
T03
T04
T05
U03
T01
T02
T03
T04
T05
U04
T01
T02
T03
T04
T05
U05
T01
T02
T03
T04
T05
U06
T01
T02
T03
T04
T05
U07
T01
T02
T03
T04
T05
U08
T01
T02
T03
T04
T05
U09
T01
T02
T03
T04
T05
F11 | [5 empty] | Ratings and feedback for product and sellers | F01, F04
U01
T01
T02
T03
T04
T05
U02
T01
T02
T03
T04
T05
U03
T01
T02
T03
T04
T05
U04
T01
T02
T03
T04
T05
U05
T01
T02
T03
T04
T05
U06
T01
T02
T03
T04
T05
U07
T01
T02
T03
T04
T05
U08
T01
T02
T03
T04
T05
U09
T01
T02
T03
T04
T05
F12 | [5 empty] | Automatic bid | F01, F04, F08
U01
T01
T02
T03
T04
T05
U02
T01
T02
T03
T04
T05
U03
T01
T02
T03
T04
T05
U04
T01
T02
T03
T04
T05
U05
T01
T02
T03
T04
T05
U06
T01
T02
T03
T04
T05
U07
T01
T02
T03
T04
T05
U08
T01
T02
T03
T04
T05
U09
T01
T02
T03
T04
T05
F13 | [5 empty] | Social media share | F04
U01
T01
T02
T03
T04
T05
U02
T01
T02
T03
T04
T05
U03
T01
T02
T03
T04
T05
U04
T01
T02
T03
T04
T05
U05
T01
T02
T03
T04
T05
U06
T01
T02
T03
T04
T05
U07
T01
T02
T03
T04
T05
U08
T01
T02
T03
T04
T05
U09
T01
T02
T03
T04
T05
F14 | [5 empty] | Wish List or Watch List for a product | F01, F02, F04
U01
T01
T02
T03
T04
T05
U02
T01
T02
T03
T04
T05
U03
T01
T02
T03
T04
T05
U04
T01
T02
T03
T04
T05
U05
T01
T02
T03
T04
T05
U06
T01
T02
T03
T04
T05
U07
T01
T02
T03
T04
T05
U08
T01
T02
T03
T04
T05
U09
T01
T02
T03
T04
T05
F15 | [5 empty] | Buy now (instead of bidding) | F01, F02, F04
U01
T01
T02
T03
T04
T05
U02
T01
T02
T03
T04
T05
U03
T01
T02
T03
T04
T05
U04
T01
T02
T03
T04
T05
U05
T01
T02
T03
T04
T05
U06
T01
T02
T03
T04
T05
U07
T01
T02
T03
T04
T05
U08
T01
T02
T03
T04
T05
U09
T01
T02
T03
T04
T05
F16 | [5 empty] | Sellers can advert on main page? Featured | F01, F04, F05
U01
T01
T02
T03
T04
T05
U02
T01
T02
T03
T04
T05
U03
T01
T02
T03
T04
T05
U04
T01
T02
T03
T04
T05
U05
T01
T02
T03
T04
T05
U06
T01
T02
T03
T04
T05
U07
T01
T02
T03
T04
T05
U08
T01
T02
T03
T04
T05
U09
T01
T02
T03
T04
T05
F17 | [5 empty] | Subscription and newsletters? | F01
U01
T01
T02
T03
T04
T05
U02
T01
T02
T03
T04
T05
U03
T01
T02
T03
T04
T05
U04
T01
T02
T03
T04
T05
U05
T01
T02
T03
T04
T05
U06
T01
T02
T03
T04
T05
U07
T01
T02
T03
T04
T05
U08
T01
T02
T03
T04
T05
U09
T01
T02
T03
T04
T05
F18 | [5 empty] | Purchace History | F01, F04
U01
T01
T02
T03
T04
T05
U02
T01
T02
T03
T04
T05
U03
T01
T02
T03
T04
T05
U04
T01
T02
T03
T04
T05
U05
T01
T02
T03
T04
T05
U06
T01
T02
T03
T04
T05
U07
T01
T02
T03
T04
T05
U08
T01
T02
T03
T04
T05
U09
T01
T02
T03
T04
T05
F19 | [5 empty] | Product tags for catigory and related | F04
U01
T01
T02
T03
T04
T05
U02
T01
T02
T03
T04
T05
U03
T01
T02
T03
T04
T05
U04
T01
T02
T03
T04
T05
U05
T01
T02
T03
T04
T05
U06
T01
T02
T03
T04
T05
U07
T01
T02
T03
T04
T05
U08
T01
T02
T03
T04
T05
U09
T01
T02
T03
T04
T05
F20 | [5 empty] | Support (tech or selling or purchasing)
U01
T01
T02
T03
T04
T05
U02
T01
T02
T03
T04
T05
U03
T01
T02
T03
T04
T05
U04
T01
T02
T03
T04
T05
U05
T01
T02
T03
T04
T05
U06
T01
T02
T03
T04
T05
U07
T01
T02
T03
T04
T05
U08
T01
T02
T03
T04
T05
U09
T01
T02
T03
T04
T05

## Iteration 0
Things | Notes / Answers
Sprint Backlog tool | Choose, create labels and columns | Trello
Architecture | tech stack, spikes as necessary. Is this a client-server, or just a web site? Does it have a database? What is tech stack? | webpage, server, database
Training | who needs to learn what, when? What are best sources for learning? | HTML, JS, PHP
Version Control | Set up (github), branches, projects, invites, etc | Folders?
Set up build system | prove you can build something (e.g. "hello world") | Sever running
Scrums | How are we going to meet? When (specifically)? Where do we post? | MWF 7: 30pm generally

## Team
Name | Email | Discord | Role | Whatever?
Jose Diaz | jdiaz86@csu.fullerton.edu | jdiaz001 | QA Tester | some knowlege in java, python, and c++
Euri Tanaka | euri_tanaka@csu.fullerton.edu / eurimagic@gmail.com | Seitenmaou(Euri) | Scrum Master | Some knowlege in Full stack, cybersecurity, Database, server stuff, C++, Java, html, JS, React, python
Kaung Khant Thaw | kthaw@csu.fullerton.edu | kkt#9474 | Tech Lead | Coding in Java, C++ and Python. Not rly good but can try :)
Julio Villegas | juliovillegas@csu.fullerton.edu | Julio Villegas #1060 | Tech Chaser | Coding in C/c++ . Linux servers (web, mail)
Daniel Wu | d.wu@csu.fullerton.edu | danielwu #9125 | Product Owner | I can help coding in C, C++, Python, VB, Java, asp.net

## Definition of Done
Item | Details, examples
fully coded
merged into github
Functional
Perfect(as bug-proof as possible)
^ QA approved
documentation | functions need documentation to help understand the input/output and/or bugs