## Product Description
Product name | WeVolunteer
Elevator Pitch | Do you have a group that wants to organize their help of the community? WeVolunteer helps people track what the needs and opportunities are and schedule the actual work. Your community adds a need and it is seen by your group so they can leap into action.
Initial Features
1 | Add a request for help, along with contact information and details.
2 | Subscribe to notifications about new requests for help and updates on existing situations
3 | Track who is volunteering for a situation, and help group members remember via calendars and notifications
4 | Users can give feedback about where they can be bought
5 | Close out requests for help after they are fulfilled
6 | Add notes about situations, such as questions and details, photos, and checklists
7 | Join and leave the group, and update contact details
Roles |  | Description
1 | Browser | Anonymous visitors - Take a look on what the community has to offer without registering.
2 | Volunteer | registered user with not much experience who will give a help
3 | Organizer | registered user with experience to share, leader of team, can provide a list of materials needed,...
4 | Community manager | Moderator - Delete inappropiate items, comments and bans users that do not abide by the rules
5 | Requester | registered user who will suggest a work, set a date to start/end, set location, set conditions, teams size, appoint an Organizer for the event

## Product backlog
Feature | User Stories | Priority | Complexity | Description
F01 |  | 1 |  | Add a request for help, along with contact information and details.
| US0101 |  | 1 | User can request help by adding information about the work (how big is the project, location, expertise neeed?, type of work, how many people needed)
| US0102 |  | 3 | User can set the work as a repetive task
F02 |  | 3 |  | Subscribe to notifications about new requests for help and updates on existing situations
| US0201 |  | 5 | Requester will receive an update about their tasks (when a worker join their work)
| US0202 |  | 5 | User will receive an update when new a new work is posted (for repetivive task)
| US0203 |  | 1 | User will receive an update when accepted jobs changed
F03 |  | 3 |  | Track who is volunteering for a situation, and help group members remember via calendars and notifications
| US0301 |  | 1 | Requester can check how many users are volunteering (and their usernames)
| US0302 |  | 3 | Requester can set a flag at event to create a calender event
| US0303 |  | 5 | Requester can set a flag at event to send a notification (SMS, email, call)
F04 |  | 4 |  | Users can give feedback about where they can be bought
| US0401 |  | 1 | Volunteer can give a feedback about the work they helped.
F05 |  | 2 |  | Close out requests for help after they are fulfilled
| US0501 |  | 3 | Requester can set a flag to stop sharing the post after the event date
| US0502 |  | 3 | Requester can set a flag to stop accepting new volunteers when the limit is reached
| US0503 |  | 3 | Requester can set a limit to how many volunteer is needed for the work
F06 |  | 2 |  | Add notes about situations, such as questions and details, photos, and checklists
| US0601 |  | 1 | Requester can add information to their requests like work conditions, details
| US0602 |  | 1 | Volunteer can ask for working conditions that would affect their help (like allergic to polen)
| US0603 |  | 3 | Volunteer can browse through photos to have an idea of the work conditions
| US0604 |  | 5 | Requester can add a checklist of required skills or conditions needed for the volunteer (no allergic to pollen, need to lift heavy objects, speak spanish…)
F07 |  | 3 |  | Join and leave the group, and update contact details
| US0701 |  | 5 | Requester can classify their job in several areas (garden, personal assistance, elderly care, home improvement, vehicles, pet care,…)
| US0702 |  | 3 | Volunteer can select from helping areas that they would like to help.
| US0703 |  | 8 | Volunteer will receive a notification when new works is posted in their groups
| US0704 |  | 8 | Requester can create a group within their post volunteer and send specific notes to them
| US0705 |  | 3 | Volunteer can opt to join and leave this group
| US0706 |  | 1 | Requester and volunteer can update their contact details
F08 |  | 1 |  | Provide a list of requests for help/work
| US0801 |  | 5 | Volunteer can display a list of work near their location
| US0802 |  | 3 | Volunteer can display a list of work based on what their like to do
| US0803 |  | 3 | Volunteer can display a list of work based on days
F09 |  | 5 |  | report a request as inappropriate / dangerous / suspicious
| US0901 |  | 3 | Registered users can report suspicious requests, abusive conditions, illegal activities,…
| US0902 |  | 3 | Volunteers can report a work that is closer to an unreported employment, demands paid training, scams
| US0903 |  | 1 | Reporting request will provide points
F10 |  | 4 |  | report a user as toxic / not appropriate as a volunteer /
| US1001 |  | 3 | Registered users can report other registered user that do not behave properly (racism, sexual harassment, bullying,,,)
| US1002 |  | 1 | reporting users will provide points
US1003
F11 |  | 4 |  | Get points when you checkin at an event
| US1101 |  | 5 | Allows user to do checkins at an event (with Requester) to get points
| US1102 |  | 1 | Registered users will be ranked according to their points (newcomer, apprentice, …)
F12 |  | 4 |  | Get more point by posting works
| US1201 |  | 3 | Allows user to request for help and increase their points
| US1202 |  | 3 | Requester could get points for each volunteer present
F13 |  | 1 |  | create you own profile / account
| US1301 |  | 3 | Users can register into the platform
F14 |  | 1 |  | User can accept a work
| US1401 |  | 3 | Volunteer cannot accept two jobs that have schedule conflicts
| US1402 |  | 1 | Only registered users can accept a work

## Release points
version | Features
1 | all features from priority 1
2 | all features priority 2
3 | all features priority 3
4 | 2-3 features priority 4
5 | remaining features priority 4
6 | priority 5 features

## UX concept
find work | suggest a work | detailed description